## Sheet1
Task Name | Ts(Week/Day) | Optimistic Activity Time(week) | Pessismistic Activity Time (week) | Most Likely Activity Time(week) | Weighted Average Actiwity(week) | Variance
1.1.5Monitor pilot and close project | 3(21) | 20 | 21 | 23 | 21.17 | 0.0278
1.3.2 Research Canadian Regulation | 3(21) | 19 | 20 | 22 | 20.17 | 0.0278
1.3.3 Identify target users & Strategy | 2(14) | 13 | 14 | 15 | 15.3 | 0.0278
1.3.6 Reserve audit requirement | 2(14) | 13 | 14 | 17 | 14.3 | 0.0278
1.5.3 Run penetration test & attack simulations | 3(21) | 19 | 20 | 26 | 20.83 | 0.0278
1.2.1 Select blockchain infrastructure | 2(14) | 12 | 14 | 17 | 14.17 | 0.1111
1.2.2 Set up Cloud Dev | 2(14) | 13 | 15 | 16 | 14.83 | 0.1111
1.2.3 Implement Consensus mechaism | 3(21) | 19 | 21 | 25 | 21.33 | 0.1111
1.4.2 Draft and publish white paper | 3(21) | 19 | 21 | 23 | 21 | 0.1111
1.4.3 Produce marketing campaign media | 3(21) | 20 | 22 | 27 | 22.5 | 0.1111
1.6.4 Provide beta user Credits & Monitor metrics | 3(21) | 19 | 21 | 27 | 21.67 | 0.1111
1.1.4Launch CADC on main net | 2(14) | 11 | 14 | 15 | 13.67 | 0.25
1.2.5 Allocate budget & 10% Contingency | 2(14) | 12 | 15 | 20 | 15.3 | 0.25
1.3.1 Analyze Blockchain Ecosytems | 3(21) | 18 | 21 | 23 | 20.83 | 0.25
1.3.4 Assess competing sublecoins | 2(14) | 11 | 14 | 16 | 13.83 | 0.25
1.3.5 Define CADC peg Methanism | 3(21) | 18 | 21 | 24 | 21 | 0.25
1.5.1 Conduct internal code audits | 3(21) | 18 | 21 | 23 | 20.83 | 0.25
1.5.2 Implement multi-sig | 2(14) | 11 | 14 | 17 | 14 | 0.25
1.6.1Design trading interface | 3(21) | 18 | 21 | 23 | 20.83 | 0.25
1.6.3 Launch governance token | 2(14) | 11 | 14 | 19 | 14.33 | 0.25
1.1.3Approve Project Objectives | 2(14) | 11 | 15 | 16 | 19.5 | 0.4444
1.2.4 Configure Developer Environment | 2(14) | 10 | 14 | 19 | 14.17 | 0.4444
1.4.1 Polish brand identity | 2(14) | 10 | 14 | 22 | 14.67 | 0.4444
1.4.4 Plan community-building events | 2(14) | 10 | 14 | 17 | 18.5 | 0.4444
1.1.2 Identify Stakeholders | 2(14) | 9 | 14 | 20 | 14.17 | 0.6944
1.6.2 Test Contracts and Dex on testnet | 3(21) | 16 | 21 | 25 | 20.83 | 0.6944
1.1.1 Draft Project Charter | 2(14) | 7 | 14 | 25 | 14.67 | 1.3611
1.5.4 Enagage independent security audit | 3(21) | 13 | 22 | 29 | 21.67 | 2.25
Sum |  | 400 | 486 | 591
2.25

## Sheet2
Task Name | Ts(Week/Day) | Optimistic Activity TimeWeek/Day) | Pessismistic Activity Time (Week/Day) | Most Likely Activity TimeWeek/Day) | Weighted Average ActiwityWeek/Day) | Variance
1.1.1 Draft Project Charter | 2(14) | 7 | 14 | 25 | 14.67
1.1.2 Identify Stakeholders | 2(14) | 9 | 14 | 20 | 14.17
1.1.3Approve Project Objectives | 2(14) | 11 | 15 | 16 | 19.5
1.1.4Launch CADC on main net | 2(14) | 11 | 14 | 15 | 13.67
1.1.5Monitor pilot and close project | 3(21) | 20 | 21 | 23 | 21.17
1.2.1 Select blockchain infrastructure | 2(14) | 12 | 14 | 17 | 14.17
1.2.2 Set up Cloud Dev | 2(14) | 13 | 15 | 16 | 14.83
1.2.3 Implement Consensus mechaism | 3(21) | 19 | 21 | 25 | 21.33
1.5.1 Conduct internal code audits | 3(21) | 18 | 21 | 23 | 20.83
1.5.2 Implement multi-sig | 2(14) | 11 | 14 | 17 | 14
1.5.3 Run penetration test & attack simulations | 3(21) | 19 | 20 | 26 | 20.83
1.5.4 Enagage independent security audit | 3(21) | 13 | 22 | 29 | 21.67
1.6.3 Launch governance token | 2(14) | 11 | 14 | 19 | 14.33
1.6.4 Provide beta user Credits & Monitor metrics | 3(21) | 19 | 21 | 27 | 21.67
Sum in Days | 238 | 193 | 240 | 298 | 246.84
Sum in Week | 34 | 27.5714 | 34.2857 | 42.5714 | 35.2629

## Sheet4
Task ID | Description | Imapct | Likelyhood
1.1.1 | Delay in formalizing the project charter may lead to scope ambiguity, authorization delays, or misalignment of contractual deliverables. | 5 | 5 | 25
1.1.2 | Insufficient stakeholder identification may result in requirement volatility and contractual misinterpretation during later phases. | 5 | 4 | 20 | Risk ID | Strategy | Strategy Description
1.1.3 | Delays in objective approval may hinder baseline establishment and disrupt subsequent milestone authorization. | 5 | 3 | 15 | 1.1.1 | Avoid | Avoid by scheduling an early charter drafting workshop with key stakeholders and requiring formal approval at a fixed milestone to lock scope and authorization before subsequent work packages begin.
1.1.4 | Late deployment to the main net may lead to contractual non-compliance, reduced functional acceptance, or integration slippage. | 5 | 3 | 15 | 1.1.2 | Avoid | Avoid by standardizing the developer environment through validated configuration templates and automated setup scripts to eliminate misconfiguration risk during early development stages.
1.1.5 | Insufficient monitoring of project closure activities may cause outstanding deliverables, audit discrepancies, or post-deployment risks. | 5 | 2 | 10 | 1.4.4 | Avoid | Avoid by preparing community-engagement events on fixed lead times with pre-approved logistics, content plans, and contingency arrangements to reduce the likelihood of delay or cancellation.
1.2.1 | Misalignment between selected architecture and regulatory or performance requirements may affect system stability and contractual compliance. | 5 | 2 | 10 | 1.5.4 | Avoid | Avoid by engaging the independent security auditor early, agreeing on assessment scope and timing contractually, and allocating a dedicated remediation team to address findings rapidly and prevent schedule slippage.
1.2.2 | Improper cloud configuration may result in security exposure, resource misallocation, or deviation from technical specifications. | 5 | 2 | 10
1.2.3 | Consensus design flaws may introduce downstream functional inconsistencies or compromise validation throughput. | 5 | 2 | 10
1.2.4 | Environment misconfiguration may delay developer onboarding and impede compliance with standardized development workflows. | 5 | 4 | 20
1.2.5 | Ineffective resource allocation may reduce financial resilience and increase exposure to cost overrun. | 5 | 3 | 15
1.3.1 | Incorrect ecosystem assessment may impair competitive positioning and lead to strategic misalignment. | 4 | 3 | 12
1.3.2 | Incomplete regulatory analysis may cause future compliance gaps and constraints in deployment. | 4 | 1 | 4
1.3.3 | Misinterpretation of target user groups may undermine adoption projections and degrade strategic fit. | 4 | 1 | 4
1.3.4 | Poor assessment of competitors may impair pricing logic and weaken market-entry viability. | 4 | 3 | 12
1.3.5 | Peg mechanism deficiencies may introduce volatility exposure and reduce stakeholder confidence. | 4 | 3 | 12
1.3.6 | Delays or inaccuracies in reserve audit planning may lead to reporting inconsistencies or certification delays. | 4 | 1 | 4
1.4.1 | Brand misalignment may reduce user trust and impair communication effectiveness across stakeholder segments. | 5 | 3 | 15
1.4.2 | Incomplete or delayed publication may affect regulatory acceptance and hinder investor due diligence. | 5 | 2 | 10
1.4.3 | Ineffective campaign assets may fail to meet requirement traceability or stakeholder communication needs. | 5 | 2 | 10
1.4.4 | Event preparation delays may reduce outreach effectiveness and impair community-engagement milestones. | 5 | 4 | 20
1.5.1 | Insufficient audit coverage may expose security vulnerabilities or compromise functional assurance. | 5 | 3 | 15
1.5.2 | Incorrect multi-sig integration may introduce key-management risks or downstream operational inconsistencies. | 5 | 3 | 15
1.5.3 | Limited penetration-testing scope may fail to identify high-impact threat vectors. | 5 | 1 | 5
1.5.4 | Third-party audit delays or findings may require remediation that jeopardizes milestone timelines or functional approval. | 5 | 5 | 25
1.6.1 | Misaligned UI/UX requirements may cause functional inefficiencies or user-acceptance issues. | 4 | 3 | 12
1.6.2 | Smart-contract or DEX failures during testnet validation may create remediation cycles that delay release. | 4 | 4 | 16
1.6.3 | Governance token deployment delays may impact utility activation and stakeholder participation. | 5 | 3 | 15
1.6.4 | Insufficient monitoring of early-stage metrics may reduce reliability of performance validation and user-feedback attribution. | 5 | 2 | 10
Risk ID | Strategy
1.1.1 | Avoid
1.1.2 | Avoid
1.4.4 | Avoid
1.5.4 | Avoid

## Sheet5
Risk ID | Strategy | Strategy Description
1.1.1 | Avoid | Avoid by scheduling an early charter drafting workshop with key stakeholders and requiring formal approval at a fixed milestone to lock scope and authorization before subsequent work packages begin.
1.1.2 | Avoid | Avoid by standardizing the developer environment through validated configuration templates and automated setup scripts to eliminate misconfiguration risk during early development stages.
1.4.4 | Avoid | Avoid by preparing community-engagement events on fixed lead times with pre-approved logistics, content plans, and contingency arrangements to reduce the likelihood of delay or cancellation.
1.5.4 | Avoid | Avoid by engaging the independent security auditor early, agreeing on assessment scope and timing contractually, and allocating a dedicated remediation team to address findings rapidly and prevent schedule slippage.